## Sheet1
Activity | Wk 0 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Deliverable
Project Preparation | [10 empty] | Baseline plan, Interview Schedule
Kickoff and Project Vision | [10 empty] | Interview, Workshop Notes, Project Vision and Charter
Requirements Gathering and Documentation | [10 empty] | User Personas, Scenarios, Wireframes, UseCases, Processflows, Domain model
Check point | [10 empty] | Check point - Plan, Deliverables, Status
Requirements Refinement | [10 empty] | User Personas, Scenarios, Wireframes, UseCases, Processflows, Domain model
Solution Architecture Definition | [10 empty] | Solution Architecture Document
Check point | [10 empty] | Check point - Plan, Deliverables, Status
Requirements and Architecture refinement | [10 empty] | Updated Requirements and Architecture document
Development of Implementation Roadmap & Plan | [10 empty] | Implementation Roadmap & Plan
Final deliverables and Executive Presentation | [10 empty] | Executive Presentation

## Sheet2
Activity | M 0 | M 1 | M 2 | M 3 | M 4 | M 5 | M 6 | M 7 | M 8 | M 9 | Deliverables
User Prototype Development | [10 empty] | Wireframes, User prototypes, Visual Design
Envirionment Setup | [10 empty] | Environment and Infrastructure definition and plan, procurement and setup of H/W, S/W and installation
Architectural Frameworks Development | [10 empty] | Architecture Frameworks, Templates and Standards
Iteration 1 Design, Development & QA | [10 empty] | Detailed Design, Test Cases, Test Results, QA passed module, Data conversion scripts
Iteration 2 Design, Development & QA | [10 empty] | Detailed Design, Test Cases, Test Results, QA passed module, Data conversion scripts
Iteration 3 Design, Development & QA | [10 empty] | Detailed Design, Test Cases, Test Results, QA passed module, Data conversion scripts
UAT | [10 empty] | UAT results, UAT passed system
Pilot | [10 empty] | Pilot results
Rollout Prep | [10 empty] | Rollout plan and checklist, Rehearsal, Data Conversion
Rollout | [10 empty] | Rollout metrics, Post Production monitoring and metrics